## Table 1
|  |  |  | Date | 2022-11-18
|  |  |  | Team ID | PNT2022TMID03180
|  |  |  | Project Name | Project - Real-Time River Water Quality Monitoring and Control System
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite | Steps To Execute | Test Data | Expected Result | Actual Result | Status | TC for Automation (Y/N) | BUG ID | Executed By
IBM Watson IoT Platform_TC_OO2 | Functional | IBM Cloud Service | Verify create a device in the IBM Watson IoT platform and get the device credentials. | IBM Cloud Service | 1.In IBM Cloud Service go to catalog 2.Create and launch the IBM Watson IoT Platform 3.Login to the Platform by clicking organization ID 4.Create a device & configure the device type and ID 5.Generate the API Key | Create a device & integrate with code | { "pH": 5, "temperature": 19, "turbidity": 15, "humidity": 82 } | Working as expected | Pass | YES | NIL | Velmurugan R
PythonCode_TC_OO3 | Code | Python 3.7 | Verify wheather the python code is without error by running it | Software | 1.Download the python version3.7 2.Type the program and save it with the extention .py 3.Verify it by compiling the code | import random import time import sys import ibmiotf.application import ibmiotf.device organization = "dymr4l" # repalce it with organization ID deviceType = "NodeMCU" deviceId = "2002" # repalce with device id | @smartinternz.com Connection Status Disconnected Last Connected: 15 Nov 2022 21:25 | Working as expected | Pass | YES | NIL | Velmurugan R
Node_Red_TC_004 | Non-Functional | IBM Cloud Service | Verify to create a node-red services | IBM cloud services | 1. In IBM cloud go to catalog 2. To create a Node-Red app 3. Click onto Deploy App 4. We need to connect the Node-Red with the IBM watson | We use a different typ of sensors to monitor the quality of water | Successfully created the node-red | Working as expected | Pass | NO | NIL | Velmurugan R
Web UI_TC_006 | Functional | Node-Red Service | To create a web UI to interact with user | Node-Red Service | 1. Go to Node-Red Dashboard 2. Make the necessary connection and deploy it. 3. Copy the URL and paste it in the new tab with "/ui" extention . 4. Display the value in of seensor in gauge. | To show the value of sensor running sucessfully and cntrol buttons | And as expected it shows the value of temprature,pH,turbidityand other sensors | Working as expected | Pass | NO | NIL | Velmurugan R
FastSMS Service_TC_OO7 | Functional | openweather API integration | for providing more weather related params | Software | 1.Signup to openweatherAPI 2.Create an API key 3.Use necessary calls for needed JSON | Show the JSON | appropriate JSON files | Working as expected | Pass | NO | NIL | Velmurugan R

## Table 2
Test Scenarios 1.) Verify the login cloud services 2.)Verify create a device in the IBM Watson IoT platform and get the device credentials. 3.) Verify wheather the python code is without error by running it 4.) Verify to create a node-red services 5.) Verify the events is stored in the database 6.) To create a web UI to interact with user 7.) To send SMS to the particular child's guardian |  |  | 2022-11-18
PNT2022TMID03180
Project - Real-Time River Water Quality Monitoring and Control System
[5 empty] | { "pH": 5, "temperature": 19, "turbidity": 15, "humidity": 82 } | Velmurugan R
| Python 3.7 |  | 1.Download the python version3.7 2.Type the program and save it with the extention .py 3.Verify it by compiling the code | import random import time import sys import ibmiotf.application import ibmiotf.device organization = "dymr4l" # repalce it with organization ID deviceType = "NodeMCU" deviceId = "2002" # repalce with device id | @smartinternz.com Connection Status Disconnected Last Connected: 15 Nov 2022 21:25 | Velmurugan R
|  |  | 1. In IBM cloud go to catalog 2. To create a Node-Red app 3. Click onto Deploy App 4. We need to connect the Node-Red with the IBM watson | We use a different typ of sensors to monitor the quality of water |  | Velmurugan R
|  |  | 1. Go to Node-Red Dashboard 2. Make the necessary connection and deploy it. 3. Copy the URL and paste it in the new tab with "/ui" extention . 4. Display the value in of seensor in gauge. | To show the value of sensor running sucessfully and cntrol buttons | And as expected it shows the value of temprature,pH,turbidityand other sensors | Velmurugan R
| openweather API integration | for providing more weather related params | 1.Signup to openweatherAPI 2.Create an API key 3.Use necessary calls for needed JSON | Show the JSON | appropriate JSON files | Velmurugan R